## Data Move
Task Name | Duration | Predecessors | Resource Names
Planning Move | 30 days
Document requirements | 25 days
Identify requirements | 10 days
Draft budget | 15 days | 3 | Relo PM
Review requirements with management | 1 day
Choose new location | 30 days
Evaluate lease sites | 30 days
Identify potential sites | 10 days | 3 | Relo PM
Identify tenant improvements | 7,5 days |  | Office manager;Relo PM
Obtain estimates for tenant improvements | 5 days |  | Office manager
Select site | 5 days | 4 | Relo PM
Finalize lease | 5 days |  | Relo PM
Identify costs | 10 days
Identify additional costs (furniture, equipment) | 10 days |  | Relo PM
Hire contractors for major tenant improvements | 5 days | 10 | Relo PM
Planning complete | 0 days | 8;9;11;12;14;15
Construct and set up space | 83 days | 16
Prep phone system | 5 days | 16
Review phone system requirements | 3 days |  | Telecom admin
Order new phone numbers | 1 day | 19 | Telecom admin
Order long-distance service | 1 day | 20 | Telecom admin
Phone lines ordered | 0 days | 21
Design and construction | 83 days
Design space | 51 days
Design office space | 10 days | 16 | Office manager[50%];Architect
Prepare drawings | 5 days | 25 | Architect
Design IT infrastructure | 10 days | 26 | Network mgr
Obtain final budget estimates | 10 days | 27
Sign off on plans | 1 day | 28
Obtain permits | 3 wks | 29
Construction | 20 days | 30
Demolish walls | 5 days
Construct new walls | 15 days | 32
Elec, mech, HVAC | 15 days | 32
Walkthrough and repair | 12 days | 33;34
Repair issues | 5 days
Schedule open house for employees | 1 day | 36 | Relo PM;Office manager
Clean new office | 1 day | 36 | Cleaning service
Construction complete | 0 days | 38
Open house | 1 day | 37;39FS+5 days

## Resources
Resource Name | Type | Material Label | Initials | Group | Max. Units | Std. Rate | Ovt. Rate | Cost/Use | Accrue At | Base Calendar | Code
Relo PM | Work |  | RPM |  | 100% | 1.000,00 kr./hr | 1.500,00 kr./hr | 0 | Prorated | Standard
Office manager | Work |  | OM |  | 100% | 1.500,00 kr./hr | 2.000,00 kr./hr | 0 | Prorated | Standard
Telecom admin | Work |  | TA |  | 100% | 1.000,00 kr./hr | 1.500,00 kr./hr | 0 | Prorated | Standard
Architect | Work |  | AR |  | 100% | 2.000,00 kr./hr | 2.500,00 kr./hr | 0 | Prorated | Standard
Network mgr | Work |  | NM |  | 100% | 1.500,00 kr./hr | 2.000,00 kr./hr | 0 | Prorated | Standard
Cleaning service | Work |  | CS |  | 100% | 800,00 kr./hr | 1.200,00 kr./hr | 0 | Prorated | Standard